## Multiple Choiec
_ amount | total slack | _ is the amount of time an activity can be delayed from its early start without delaying the planned project finish date
_ by | risk mitigation | _ involves reducing the impact of a risk event by reducing the probability of its occurrence
_ deciding | planning risk management | _ involves deciding how to approach and plan the risk management activities for the project
_ lists | probability or impact matrix | the _ lists the relative probability of a risk occurring and the relative impact of the risk occurring
_ predefined | contingency plans | _ are predefined actions that the project team will take if an identified risk event occurs
_ technique | design of experiments | _ is a technique that helps identify which variables have the most influence on the overall outcome of a process
acceptable | appraisal cost | _ is the cost of evaluating processes and their outputs to ensure that a project is error-free or within an acceptable error range
accepting | user acceptance testing | _ is an independent test performed by end users prior to accepting the delivered system
achieves | risk-neutral | a _ person achieves a balance between risk and payoff
affect | identifying risks | _ involves determining which risks are likely to affect a project and documenting the characteristics of each
after working | estimate the duration of activities | after working with key stakeholders to define activities and calculate their resources the next process in project time management is to
allocate | budgetary | a cost estimation tool which is used to allocate money into an organizationâ€™s budget is known as a _ estimate
an done | unit test | an _ is done to test each individual component often a program to ensure that it is as defect-free as possible
analogous also | top-down | analogous estimates are also known as _ estimates
analyses | planning | performing qualitative and quantitative risk analyses are subprocesses of the _ process of project risk management
analyzing | developing the schedule | in project time management which of the following processes involve analyzing activity sequences activity resource estimates and activity duration estimates to create the project schedule
aoa network | finish-to-start | aoa network diagrams use only _ dependencies
applies | risk acceptance | _ applies to positive risks when the project team cannot or chooses not to take any actions toward a risk
approximation | estimating costs | which of the following involves developing an approximation of the costs of resources needed to complete a project
attribute | an activity attribute provides more schedule-related information about each activity than an activity list | which of the following is a difference between an activity list and an activity attribute
awards | definitive | if the cost estimate for a project is a basis for contract awards and performance reporting it should be an _ estimate and as accurate as possible
bell | normal distribution | a _ is a bell-shaped curve that is symmetrical regarding the average value of the population the data being analyzed
boxes | pdm | a network diagramming technique in which boxes represent activities is known as an _
calculating | estimating activity durations | in project time management which of the following processes involve calculating the number of work periods that are needed to complete individual activities
changes _ | monitoring and controlling | validated changes and validated deliverables are the outputs of the _ subprocess of project quality management
choosing | statistical sampling | _ involves choosing part of a population of interest for inspection
completes | project cost management | _ includes the processes required to ensure that a project team completes a project within an approved budget
continuous | iso 9000 | _ a quality system standard is a three-part continuous cycle of planning controlling and documenting quality in an organization
corrects | process adjustments | _ corrects or prevents further quality problems based on quality control measurements
cost variance is | the earned value minus the actual cost | cost variance is
decision | influence diagram | an _ represents decision problems by displaying essential elements including decisions uncertainties causality and objectives and how they influence each other
defining project activities | determining their dependencies | in project time management the next step after defining project activities is
deming | eliminate the annual rating or merit system | which of the following is one of demingâ€™s 14 points for management
description | define | important tools used in the _ phase of the dmaic process include a project charter a description of customer requirements process maps and voice of the customer voc data
develop | life cycle costing | _ helps develop an accurate projection of a projectâ€™s financial expenses and benefits
difficult | intangible costs | _ are those costs that are difficult to measure in monetary terms
draft | project charter | a draft schedule for a project is most likely to be found in a _
ease | maintainability | _ addresses the ease of performing maintenance on a product
enhance | planning risk responses | _ involves taking steps to enhance opportunities and reduce threats to meeting project objectives
establish | determining the budget | _ involves allocating the overall cost estimate to individual work items to establish a baseline for measuring performance
estimated | cash flow analysis | _ is a method for determining the estimated annual costs and benefits for a project
evaluation | pert uses different duration estimates whereas cpm uses one specific duration estimate | a difference between the program evaluation and review technique pert and critical path method cpm is that
expands | parkinsonâ€™s law | _ states that work expands to fill the time allowed
fact | interviewing | _ is a fact-finding technique that can be used for collecting information in face-to-face phone e-mail or instant-messaging discussions
fault | six 9s of quality rule | the _ is a measure of quality control equal to 1 fault in 1 million opportunities problems
finsih | it is a dependency in which the â€œfromâ€ activity must be finished before the â€œtoâ€ activity can be finished | which of the following is true of a finsih-to-finish dependency
first project | to plan how costs will be managed | the first step in project cost management is
fishbone | analyze | an important tool used in the _ phase of the dmaic process is the fishbone or ishikawa diagram
five | dmaic | projects that use six sigma principles for quality control normally follow a five-phase improvement process called _
footwear | electricity used to run its factories | soles is a footwear company which has recently set up its store in ambrosia to manufacture its products soles incurs a range of different costs which of the following would be an example of an indirect cost
forecasts | cost control | work performance information and cost forecasts are main outputs of the _ process
function | functionality | _ is the degree to which a system performs its intended function
generate | defining activities | in project time management which of the following processes generate the main outputs of an activity list activity attributes and a milestone list
generates | benchmarking | _ generates ideas for quality improvements by comparing specific project practices or product characteristics to those of other projects or products within or outside the performing organization
good | sunk | good earth a company manufacturing packaged food products sets up its stores in baltonia however a year later the company closes the store down due to high operating costs in such a scenario the money spent in paying for the rent of the store in baltonia would be an example of _ costs
graphic | control chart | a _ is a graphic display of data that illustrates the results of a process over time
hires | direct | newtech inc hires john for the position of a software programmer to work on their new project salary paid to john by newtech inc would be an example of _ costs
identifying risks | planning | identifying risks is a subprocess of the _ process of project risk management
immediately | free slack | the amount of time an activity can be delayed without delaying the early start date of any immediately following activities is known as a _
impede | negative | potential problems that might occur on the project and how they might impede project success are _ risks
implementing | secondary | _ risks refer to those that are direct results of implementing risk responses
in _ | project management plan update | in project time management an _ is an output of controlling the schedule
in which | sequencing activities | in project time management which of the following processes primarily involve identifying and documenting the relationships between project activities
indirect costs | not directly related to the products or services of a project | indirect costs are
inherent | mandatory | which of the following types of dependencies are inherent in the nature of work being performed on a project
instance | defect | an _ is any instance where the product or service fails to meet customer requirements
integrate | cmmi | _ helps integrate traditionally separate organizational functions set process improvement goals and priorities provide guidance for quality processes and provide a point of reference for appraising current processes
involved | planning schedule management | the first process involved in project time management is _
juran | an organization should build awareness of the need and opportunity for improvement | one of juranâ€™s ten steps to quality improvement states that
latest | late start date | the _ for an activity is the latest possible time an activity might begin without delaying the project finish date
main goal | cost budgeting | the main goal of the _ process is to produce a cost baseline for measuring project performance and project funding requirements
maintains | top ten risk item tracking | _ are or is a qualitative risk analysis tool that maintains an awareness of risks throughout the life of a project in addition to identifying risks
measurement | metric | a _ is a standard of measurement in quality management
members | defining activities | which of the following processes in project time management involves identifying the specific tasks that the project team members and stakeholders must perform to produce the project deliverables
metrics | planning quality management | process improvement plan quality metrics and quality checklists are the outputs of the _ process of project quality management
normal | reliability | _ is the ability of a product or service to perform as expected under normal conditions
numerically | performing quantitative risk analysis | _ involves numerically estimating the effects of risks on project objectives
obtain | crashing | the technique for making cost and schedule trade-offs to obtain the greatest amount of schedule compression for the least incremental cost is known as _
of_ | controlling the schedule | in project time management the process of_ primarily involves checking and managing changes to the project schedule
one _ | cost budgeting | one of the main outputs of the _ process is a cost baseline
opportunity | risk enhancement | _ involves changing the size of the opportunity by identifying and maximizing key drivers of the positive risk
output process | cost forecasts | which of the following is an output of the process of controlling costs
ownership | risk sharing | _ involves allocating ownership of the risk to another party
parallel | fast tracking | which of the following techniques involve doing activities in parallel that one would normally do in sequence
pareto | quality control | the _ process is often associated with the technical tools and techniques of quality management such as pareto charts quality control charts and statistical sampling
performing assurance | executing | performing quality assurance is a subprocess of the _ process of project quality management
previous | analogous estimates | which of the following types of estimate use the actual cost of a previous similar project as the basis for estimating the cost of the current project
prioritizing | performing qualitative risk analysis | _ involves prioritizing risks based on their probability and impact of occurrence
process primarily | managing changes to the project budget | the process of controlling costs primarily involves
procurement | resource calendars | in project procurement management which of the following is an output of the executing process
profits | revenues minus expenditures | profits may be defined as
protects | feeding buffers | critical chain scheduling protects tasks on the critical chain from being delayed by using _ which consist of additional time added before tasks on the critical chain that are preceded by non-critical-path tasks
provides | gantt charts | _ provides a standard format for displaying project schedule information by listing project activities and their corresponding start and finish dates in a calendar format
purchasing | definitive | a _ estimate is used for making many purchasing decisions for which accurate estimates are required and for estimating final project costs
reason | people lack estimating experience | which of the following is most likely to be a reason for inaccuracies in information technology cost estimates
refers | rework | _ refers to action taken to bring rejected items into compliance with product requirements or specifications or other stakeholder expectations
relates | external failure cost | _ is a cost that relates to all errors not detected and not corrected before delivery to the customer
relationship | start-to-start | which of the following is a relationship in which the â€œfromâ€ activity cannot start until the â€œtoâ€ activity is started
residual | controlling risk | _ involves monitoring identified and residual risks identifying new risks carrying out risk response plans and evaluating the effectiveness of risk strategies throughout the life of the project
rough can | ballpark | a rough order of magnitude estimate can be referred to as a _ estimate
schedule variance | the earned value minus the planned value | schedule variance is
select | decision tree | an _ is a diagramming analysis technique used to help select the best course of action in situations in which future outcomes are uncertain
serve | project charter | which of the following documents is most likely to include planned project start and end dates which serve as the starting points for a detailed schedule
shifting | risk transference | _ involves shifting the consequence of a risk and responsibility for its management to a third party
show | sensitivity analysis | a _ is a technique used to show the effects of changing one or more variables on an outcome
sigmas | 3.4 | six sigmas target for perfection is the achievement of no more than _ defects errors or mistakes per million opportunities
significant | milestone | an _ on a project is a significant event that normally has no duration
silimarity | both are portions of the integrated change control process under project integration management | which of the following is a silimarity between scope control and schedule control
similarity | both can shorten the time needed to finish a project | a similarity between the crashing technique and the fast tracking technique is that
simulates | monte carlo | _ analysis simulates a modelâ€™s outcome many times to provide a statistical distribution of the calculated results
slack | longest; shortest | the critical path is the _ path through a network diagram and it represents the _ amount of slack or float
sometimes | discretionary | _ dependencies are sometimes referred to as soft logic and should be used with care because they may limit later scheduling options
special | features | _ are the systemâ€™s special characteristics that appeal to users
spi | it can be used to estimate the projected time to complete the project | which of the following is true of the schedule performance index spi
subtracting | earned value | variances are calculated by subtracting the actual cost from _
summing | bottom-up | a cost estimation tool which involves estimating individual work items or activities and summing them to get a project total is known as an _ estimate
tangible | they can be easily measured | which of the following is true of tangible costs
the cpi | can be used to estimate the projected cost of completing the project | the cost performance index cpi
threat | risk avoidance | _ involves eliminating a specific threat usually by eliminating its causes
two | bursts | in an aoa network diagram _ occur when two or more activities follow a single node
ultimate | developing a schedule | in project time management the ultimate goal of _ is to provide a basis for monitoring project progress for the time dimension of the project
uncertainty | risk appetite | the degree of uncertainty an entity is willing to take on in anticipation of a reward is
understanding | defining activities | in project time management the main goal of _ is to ensure that the project team has complete understanding of all the work they must do as part of the project scope so they can start scheduling the work
unenforceable | procurement | unenforceable conditions or contract clauses and adversarial relations are risk conditions associated with the project _ management knowledge area
unplanned | workarounds | _ are unplanned responses to risk events used when project teams do not have contingency plans in place
unpredictable | management reserves | which of the following reserves allows for future situations that are unpredictable
uses | parametric estimating | _ uses project characteristics in a mathematical model to estimate project costs
utility | risk-averse | risk utility rises at a decreasing rate for a _ person
values | planned value | the budget is one of the three values of earned value management and is also known as _
vital | pareto charts | _ help users to identify the vital few contributors that account for most quality problems in a system
was | fitness for use | _ means that a product can be used as it was intended
well | performance | _ addresses how well a product or service performs the customers intended use
what is | assess the range for the variables being considered | what is the first step in a monte carlo analysis
whatever | risk exploitation | _ involves doing whatever you can to make sure the positive risk happens
which analogous | they are most reliable when previous projects are similar in fact with current projects | which of the following is true of analogous estimates
which bottom | they are time-intensive and expensive to develop | which of the following is true of bottom-up estimates
which contingency | they allow for future situations that can be partially planned for | which of the following is true of contingency reserves
which dependencies | external | which of the following dependencies involve relationships between project and non-project activities
which dummy | they show logical relationships between activities | which of the following is true of dummy activities
which earned | it is an estimate of the value of the physical work actually completed | which of the following is true of earned value
which input | work performance data | which of the following is an input of the process of controlling costs
which network | critical path analysis | which of the following is a network diagramming technique used primarily to predict total project duration
which one | project documents update | which of the following is one of the main outputs of estimating activity resources process
which rough | it provides an estimate of what a project will cost | which of the following is true of a rough order of magnitude estimate
which schedule | lessons-learned reports | which of the following is an output of schedule control
who | risk-seeking | those who are _ have a higher tolerance for risk and their satisfaction increases when more payoff is at stake
written | conformance to requirements | _ means the projects processes and products meet written specifications
wrote | crosby | _ wrote quality is free in 1979 and is best known for suggesting that organizations strive for zero defects

## True
a index | TRUE | a schedule performance index of one means that the project is on schedule
able | TRUE | it project managers must be able to present and discuss project information both in financial and technical terms
accept | TRUE | one possible response to managing negative risk it to accept the potential effects from the risk
accepted | TRUE | products that are accepted by project stakeholders are considered to be validated deliverables
accuracy | TRUE | in a bottom-up estimate the size of the individual work items is one of the factors that drives the accuracy of the estimates
agreement | TRUE | it is important for the activity list and activity attributes to be in agreement with the work breakdown structure
assurance involves | TRUE | the quality assurance process involves taking responsibility for quality throughout the projectâ€™s life cycle
become | TRUE | estimates should become more accurate as time progresses
completed | TRUE | a tracking gantt chart is based on the percentage of work completed for project tasks or the actual start and finish dates
conduct | TRUE | project managers must conduct cash flow analysis to determine net present value
contingency plans | TRUE | contingency plans are predefined actions that the project team will take if an identified risk event occurs
critical path | TRUE | the critical path on a project can change as the project progresses
definitive | TRUE | definitive estimates are made one year or less prior to project completion
delphi | TRUE | the delphi technique is a systematic interactive forecasting procedure based on independent and anonymous input regarding future events
describes | TRUE | a schedule management plan includes information which describes the format and frequency of schedule reports required for the project
determining budget | TRUE | determining the budget involves allocating the project cost estimate to individual work items over time
element | TRUE | an activity is an element of work that has an expected duration cost and resource requirements
external | TRUE | external failure cost
finishing | TRUE | the monte carlo analysis can predict the probability of finishing by a certain date or the probability that the cost will be equal to or less than a certain value
formulas | TRUE | the formulas for variances and indexes start with ev the earned value
inputs | TRUE | the project management plan and project funding requirements are inputs of the process of controlling costs
knowing | TRUE | knowing the amount of float allows project managers to know whether a project schedule is flexible
materialize | TRUE | identified risks may not materialize or their probabilities of occurrence or loss may diminish
need | TRUE | quantitative risk analysis need not be done for projects that are large and complex
parametric | TRUE | parametric models are reliable when the models are flexible in terms of the projects size
pertains | TRUE | a dependency pertains to the sequencing of project activities or tasks
preferred | TRUE | network diagrams are the preferred technique for showing activity sequencing
procedures | TRUE | a cost management plan can include organizational procedures links control thresholds and process descriptions
reasons | TRUE | one of the reasons why project cost estimates are inaccurate is because human beings are biased toward underestimation
register | TRUE | the risk register can be created with a simple microsoft word or excel file
result | TRUE | the technique of fast tracking can result in lengthening the project schedule
reviewing | TRUE | to define activities the project team should start with reviewing the schedule management plan scope baseline enterprise environmental factors and organizational processes
risks can | TRUE | risks can have both negative and positive effects on meeting project objectives
schedules | TRUE | project schedules grow out of basic documents such as the project charter
seeking | TRUE | a risk-seeking person prefers outcomes that are more uncertain and is often willing to pay a penalty to take risks
side | TRUE | a probability or impact matrix or chart lists the relative probability of a risk occurring on one side of a matrix or axis on a chart and the relative impact of the risk occurring on the other
solution | TRUE | the microsoft solution framework msf includes a risk management model that includes developing and monitoring a top-ten master list of risks
spreadsheets | TRUE | spreadsheets are a common tool for cost estimating cost budgeting and cost control
supplier | TRUE | if an important supplier goes out of business management reserves can be set aside to cover the resulting costs
supporting | TRUE | supporting details for an estimate include the ground rules and assumptions used in creating the estimate
tqc | TRUE | in tqc product quality is more important than production rates and workers are allowed to stop production whenever a quality problem occurs
ultimately | TRUE | project managers are ultimately responsible for quality management on their projects
understand | TRUE | it is important for project managers to understand that every cost estimate is unique
wide | TRUE | using six sigma principles is an organization-wide commitment and all employees must embrace its principles
works | TRUE | the six sigma approach works best for a project where a quality problem is identified between the current and desired performance

## False
100 | FALSE | if the cost performance index cpi is less than 100 percent the project is under budget
a budgetary | FALSE | a budgetary estimate is the most accurate of the three types of estimates
after developing | FALSE | after defining project activities the next step in project time management is developing the schedule
aid | FALSE | gantt charts cannot be used to aid project quality management
analogous most | FALSE | analogous estimates are the most accurate technique to estimate costs
arrows | FALSE | the arrows in a network diagram represent missed milestones in a project
aspect | FALSE | customer requirements are an important aspect of the quality planning process
assumes | FALSE | critical chain scheduling assumes that resources multitask and maximizes multitasking
backward | FALSE | a backward pass through the network diagram determines the early start and early finish dates for each activity
brainstorming is | FALSE | brainstorming is a systematic interactive forecasting procedure based on independent and anonymous input regarding future events
capacity | FALSE | a drawback of the project management software is that it does not have the capacity to calculate the critical paths for a project
changes assurance | FALSE | validated changes and validated deliverables are the outputs of the quality assurance process
costing | FALSE | analogous estimates are called activity-based costing
demarco | FALSE | demarco and listerâ€™s study on organizations and productivity found direct correlations between productivity and programming language years of experience and salary
design | FALSE | the design of experiments technique cannot be applied to project management issues such as cost and schedule trade-offs
detriment | FALSE | risk events refer to specific certain events that may occur to the detriment or enhancement of the project
disadvantage of | FALSE | a disadvantage of using gantt charts is that they do not provide a standard format for displaying planned project schedule information
disadvantages | FALSE | one of pertâ€™s main disadvantages is that it does not address the risk associated with duration estimates
easy | FALSE | milestones are easy to achieve and are always achieved through one main activity
even | FALSE | budgetary estimates are made even before a project is officially started
final process | FALSE | the final process in project time management is developing the schedule
focus | FALSE | it is important for project managers to focus on indirect costs because they can be easily controlled
frameworks | FALSE | frameworks for helping organizations improve their processes and system are called six sigma chartsâ€‹
frequently | FALSE | start-to-finish relationships are the most frequently used dependencies between activities
house | FALSE | only in-house auditors can perform quality audits
if cost | FALSE | if cost variance is a positive number it means that performing the work costs more than planned
in one | FALSE | in project time management one should control the schedule before estimating the duration for each activity
in primary | FALSE | in project time management the primary output of defining activities is a schedule management plan
intangible | FALSE | intangible costs can be easily measured in monetary terms
integration | FALSE | integration testing involves testing of each individual component to ensure that it is as defect-free as possible
invest | FALSE | when deciding what projects to invest in or continue one should include sunk costs
last | FALSE | the last step in project risk management is deciding how to address this knowledge area for a particular project by performing risk management planning
lengthens | FALSE | the main disadvantage of crashing is that it lengthens the time needed to finish a project
lower | FALSE | the lower the earned monetary value calculation for a project the chances of project success is higher
managed | FALSE | unknown risks can be managed proactively
mandatory | FALSE | in a network diagram it is mandatory for every item on the wbs to be shown instead of only those activities with dependencies
merge | FALSE | a merge occurs when one node precedes mutiple nodes
overrun | FALSE | overrun is the additional percentage amount by which estimates exceed actual costs
precedence | FALSE | a drawback of the precedence diagramming method is that it cannot be used unless dummy activities are employed
psychology | FALSE | the psychology literature shows that individuals working alone produce fewer ideas than the same individuals produce through brainstorming in small face-to-face groups
reliability | FALSE | reliability is the ability of a product or service to perform as expected under deviant conditions
request | FALSE | the primary output of the planning cost management process is a change request
right | FALSE | in an earned value chart when the actual cost line is right on or above the earned value line it indicates that costs are less than planned
run | FALSE | a run chart is a bar graph that depicts data points and their order of occurrence
shortest | FALSE | in a critical path analysis the shortest path is what drives the completion date for the project
stage | FALSE | testing as a stage is important only at the end of an information technology product development
term | FALSE | the term sigma means median
these | FALSE | in project time management the next step after sequencing activities is to define these activities
thick | FALSE | in a gantt chart thick black bars represent milestones achieved in a project
took | FALSE | a negative schedule variance means that it took lesser than planned to perform the work
top ten | FALSE | top ten risk item tracking is a quantitative risk analysis tool
unknowns | FALSE | contingency reserves are also known as unknown unknowns